## Sheet1
Planning
Tasks | LOE (Hours)
Find and review different existing websites and systems | 6
Identify all possible features for the landing page | 1.5
Find media resources that can be used for the design of the website | 2
Identify all possible parts of the system that will be affected of the enhancement | 3
Identify any tool and plugins that will be used for the enhancement | 3
Document Learning | 2
Write the SRS Document | 1.5
Write the SDS Document | 1.5
Plan and Write the time frame | 2
Plan and Write the WBS | 1.5
Subtotal for Planning | 24
Back up all files from the main server and join aubrey to configure the server | 8
Configure the production server | 1